## Plan up to event
Sample Marketing Plan and Timeline Could be used for general promotion or for a performance budget: £xxxx
Activity | Total Quoted | Total Spent | Jan |  |  |  | Feb |  |  |  | Mar |  |  |  | Apr |  |  |  | May |  |  |  | Jun |  |  |  | Jul |  |  |  | Aug
|  |  | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3
External marketing and communications
Add event details to your email footer | put quote totals in here to keep track of your budget options | then move into this column when the booking is made and the subtotals will update | bar: Mar 1
Initial announcement of event to your email mailing list (bear in mind GDPR) | bar: Mar 1
Tweet about your event using the # hashtag | bar: Mar 1 to Aug 3
Announce your event on your Facebook page. Consider using promoted posts to engage new audiences. | bar: Mar 1 to Aug 3
…don't forget about Instagram! | bar: Mar 1 to Aug 3
Is it an event for a professional audience? You might want to put LinkedIn here too. Remember to add lines and customise ypur campaign for any other social platforms you might have, like TikTok, Mastodon, etc. | bar: Mar 1 to Aug 3
Research and planning of potential promotion partners, contact other local groups to discuss joint marketing opportunities | bar: Feb 2 to Feb 3
Further emails out to all of your relevant mailing lists (bear in mind GDPR) | bar: Apr 3; May 2; Jun 2; Jul 2; Jul 4; Aug 2 to Aug 3
Direct mail to your own mailing list if appropriate and budgets allow, see marketing materials section. You can fulfill in-house with enough volunteers if you have a large list, if not, a mailing house can do this for you (bear in mind GDPR, whether in-house or externally fulfilled) | bar: Jun 2 to Jun 4
Internal marketing and communications
Initial announcement to staff | bar: Jan 3
More detailed briefing for staff, including synopsis (for shows) or a group overview (for a new youth theatre group). Could you consider a one-page A4 crib sheet for staff notice boards? | bar: Feb 2 to Feb 3
Advertising/Editorial
Start booking advertising in specialist publications, eg. Primary Times (schoolspublishing.com), Families Magazine (familiesonline.co.uk) |  |  | Feb 3: book now…; Jun 1: for summer edition of Primary Times; Jul 1: for Jul/Aug edition of Families Mag
Include event in listings to local papers | bar: Apr 3
List your event on the YTAS website | bar: Mar 2
Wanna get really fancy? Start booking external advertising space if budgets allow - especially if you can get a group of youth theatres to join together to split the cost. Billboards (jcdecaux.co.uk, clearchannel.co.uk, primesight.co.uk, exterionmedia.com, global.com - decide who has the best sites in your area) Bus shelter AdShels (jcdecaux.co.uk, clearchannel.co.uk) Bus advertising (exterionmedia.com) Train stations (exterionmedia.com, jcdecaux.co.uk) Shopping Centres, Supermarkets (jcdecaux.co.uk) |  |  | Feb 3: book now…; Jul 3: …for around here or before
Local newspaper advertising. Remember associated online advertising and promoted social posts. | bar: Jul 4 to Aug 3
Promotion through local community newsletters and magazines, editions not always frequent so be sure to check this in advance. Often posted straight through letterboxes, so keep an eye out in your area. | bar: Jul 1 to Aug 3
Radio talk-ups and competitions are a good way to get coverage without paying for a full ad campaign. Some stations have event listings where public events can be submitted to be read out on air, but there is no guarantee of this. |  |  | May 2: start planning here…; Aug 1: ...for the weeks before the event
Local newspaper editorial - are there any angles for press stories? | bar: Jun 2 to Aug 3
Distribution
Flyer and poster distribution Take One Media (takeonemedia.co.uk) and Direct Distribution (directdistribution.co.uk) cover the whole country for flyers and posters, and you can book any specific region or even specialist runs (eg Take One's Capital Culture service will distribute your flyers to all theatres, museums, galleries and other such attractions in Edinburgh) Landmark Press (landmark-press.com) specialise in the tourist guide market. To save money on courier fees, work out how many flyers are going where, and have the printer deliver them straight there. Your printer might charge for this, but it's less admin hassle for you. |  |  | Feb 3: book now…; Jun 2: ...for distribution around here
Marketing materials
Prepare a design brief for your designer. Remember to tell them all you'll need (eg specific sizes for website adverts, banners, local press dimensions, etc). If you have someone in house who can use design software, ask for the packaged files so that they can make you surveys, signage, anything else you might want to brand with your main show imagery. This will cost extra. | bar: Feb 2
Do you have space for an outdoor vinyl banner? Check with your local council to make sure they will allow it. Buying one without knowing if you're allowed to display it is an expensive gamble. Your venue may have their own sites you can use too. | bar: Mar 2 to Mar 3
Flyers and posters - use these in the local area, or for the area/market you're trying to attract. Remember to keep enough for your venue! | bar: Jun 2 to Aug 3
Do you or the venue have space for large format posters? A1, A0, 4sheet? Remember to have them designed to this size… don't enlarge A3 artwork to A1 as this will look awful. | bar: Jun 2 to Aug 3
Website updates - show listed on your website and kept up-to-date with current information | bar: Mar 4 to Aug 3
Have your data capture forms freely available and actively encourage attendees to sign up for your mailing list (see GDPR for guidance) | bar: Aug 1 to Aug 3
Direct mail letters to your mailing list | bar: Jun 2 to Jun 3
Administration costs
Website hosting, stationery, printer ink, courier charges (eg for sending flyers to the mailing house or posters to a distributor). | bar: Apr 1
SUBTOTALS | 0 | 0
TOTAL |  | 0
Some notes on VAT
Are you a registered charity? Ask suppliers if you qualify for zero VAT, then fill out the declaration forms.
Remember there's no VAT (for anybody!) on certain print items - see www.isitvatable.com for guidance.
If you're using this format to budget your project, remember to ask your bookkeeper how they'd like you to track the VAT.
We often make a 'Total Spent (NON-VATABLE)' and a 'Total Spent (VATABLE)' column, and make a formula to add VAT automatically when it applies.