## NFYT Risk Assessment
Youth Theatre Arts Scotland - NFYT Risk Assessment
Last updated: January 2026
| Impact Key |  | Probability Key
1 | No noticeable effects | 1 | Impossible in ordinary circumstances
2 | Effects can be controlled at minor cost | 2 | Unlikely unless other events precipitate
3 | Significant impact | 3 | Quite possible in ordinary circumstances
4 | Severe impact | 4 | Fairly likely especially if other factors present
5 | Permanent impact | 5 | Very high chance of occurrence
Risk Scores
0-5 = Low Risk
6-9 = Medium Risk
10-15 = High Risk
16-25 = Very High Risk
Assessment |  |  |  |  | Planning and Implementation
Code | Identified Risk (Description of risk to be managed) | Impact 1 - 5 (5 = most severe) | Probability 1 - 5 (5 = most probable) | Risk Score (probability x Impact = Priority) | Planned Response (Description of how the risk will be managed) | Impact 1 - 5 (5 = most severe) | Probability 1 - 5 (5 = most probable) | Residual Score (probability x Impact = Priority) | Risk Owner (person(s) responsible) | Monitoring
NFYT1 | Child Abuse | 5 | 3 | 15 | All young people will be supervised by vetted festival staff during core activity | 5 | 2 | 10 | CEO/ Sector Development Manager/ General Manager | CEO
All activity is governed by Youth Theatre Arts Scotland's Child Protection Policy and Code of Conduct
All festival staff will be trained in Child Protection protocol
The general public will not be given any access to young people
Young people will be supervised by their own group leaders when not engaging in core activity.
YTAS has a designated Child Protection lead who will oversee policies and procedures
All participating groups will be issued with Youth Theatre Arts Scotland's Child Protection Guidelines for NFYT and are required to complete and submit a signed Child Protection Agreement. The guidelines include a checklist for groups, our NFYT Child Protection Policy, and a Code of Conduct for group leaders. The checklist outlines the child protection measures required to be in place by each group attending.
NFYT2 | Abuse of alcohol and/or illegal drugs | 3 | 2 | 9 | There will be a total ban on alcohol and illegal drugs (applicable to all ages) | 2 | 2 | 4 | CEO/ General Manager/Projects Producer | CEO
Young people will be denied access to areas where alcohol is sold in all project venues
YTAS and Eden Court staff, Young Leaders, and Group Leaders will be instructed to remain vigilant
All participating groups will be issued with Youth Theatre Arts Scotland's NFYT Code of Conduct for participants with the expectations for safe and positive behaviour at the event, as well as the consequences of any breaches
NFYT3 | First aid incident or emergency | 3 | 3 | 9 | Appropriately qualified first aid-trained staff will be identified to cover all NFYT activity | 2 | 2 | 4 | CEO/ Production Manager/ Projects Producer | CEO
First aid equipment will be made available across all venues and campsite
NFYT4 | Injury caused because of a fire or evacuation at the venue | 5 | 2 | 10 | YTAS and Eden Court staff, Young Leaders, and Group Leaders will be briefed on venue evacuation procedures | 5 | 1 | 5 | CEO/ Production Manager/ Venue Partners | CEO
Festival staff will be governed by venue staff and procedures, where available, in such an event
Appropriately qualified first aid-trained staff will be identified to cover all NFYT activity
First aid equipment will be made available across all venues and the campsite
Group leaders and young people will be alerted of alarm-raising and evacuation procedures
NFYT5 | Injury due to accident/trip/fall at venues | 3 | 3 | 9 | Specific risk assessments will be carried out in advance of performances and relevant workshop activity | 3 | 1 | 3 | CEO/ Production Manager/ Venue Partners | CEO
All activity involving movement of people to and from events will be supervised and guided by festival staff
The general public will be guided in/out of performances by Eden Court Front of House staff
Appropriately qualified first aid-trained staff will be identified to cover all NFYT activity
First aid equipment will be made available across all venues and the campsite
NFYT6 | Injury due to physical activity | 3 | 3 | 9 | Young people will be supervised to a ratio of (at the most) 1:15 by YTAS and Eden Court staff, Young Leaders, and Group Leaders | 3 | 2 | 6 | CEO/ Sector Development Manager | CEO
Young people will be asked to wear clothing suitable for physical activity
Rooms allocated for activity will be of a suitable size and free of hazards
Appropriately qualified first aid-trained staff will be identified to cover all NFYT activity
First aid equipment will be made available across all venues and the campsite
Drinking water will be made available
NFYT7 | Stage-based injury relating to electrics or heavy equipment | 5 | 3 | 15 | All stage rigging will be undertaken by qualified professional staff | 5 | 2 | 10 | CEO/ Production Manager/ Venue Partners | Production Manager
All equipment used is in good working order and to current safety standards
Young people will receive a'Safe Stage Conduct' briefing and stage tour by the Production Manager
Young people will be supervised by production staff at all times
Young people will be supervised by their own group leaders when not engaging in core activity
Sufficient rehearsal time will be allotted to enable young people to get used to safely operating in a stage-based environment
Appropriately qualified first aid-trained staff will be identified to cover all NFYT activity
First aid equipment will be made available across all venues
NFYT8 | Injury due to accident/trip/fall at campsite | 3 | 2 | 6 | Groups will be briefed on campsite layout | 2 | 1 | 2 | CEO/ Production Manager/ Projects Producer | CEO
Large movement of young people (more than 10) will be guided by festival staff
All infrastructure brought into the campsite (e.g. shower block, generator) will be hired from and installed by experienced suppliers and check regularly onsite.
Appropriately qualified first aid-trained staff will be identified to cover all NFYT activity
First aid equipment will be made available across all venues
NFYT9 | Food-related injury (poisoning, allergic reaction, choking) | 4 | 3 | 12 | YTAS will contract approved caterers (with food hygiene certification) | 2 | 1 | 2 | Projects Producer/ Caterers | CEO
Participating groups will submit information regarding dietary requirements (including allergies) in advance of the event
Food will be clearly labelled with allergen information
Food will be served at an appropriate temperature and any hot plates will be labelled as such
Appropriately qualified first aid-trained staff will be identified to cover all NFYT activity
First aid equipment will be made available across all venues and the campsite
NFYT10 | Injury due to public disorder incident at campsite | 3 | 3 | 9 | YTAS will liaise with the Highland Council and park employees during planning | 2 | 2 | 4 | CEO/ Production Manager/ Projects Producer | CEO
YTAS will liaise with local police and communtiy officers during planning
Staff, participants and group leaders will be briefed on the event (inc. lights-out times) and code of conduct
Local emergency numbers will be made available to YTAS and Eden Court staff, Young Leaders, and Group Leaders in case of incidents
NFYT11 | Injury or illness due to adverse weather conditions at campsite (flooding, rain/flooding/heatwave) | 4 | 2 | 8 | YTAS will contract approved suppliers of campsite infrastructure, i.e. marquees, toilets/showers/generator (with insurance) | 3 | 2 | 6 | CEO/ Production Manager/ Projects Producer | CEO
YTAS will monitor weather Met Office weather information before, during and directly after the event
Security and function of campsite infrastructure will be regularly monitored by campsite wardens throughout the event
Participants will be advised in writing to bring sunscreen, water bottles and waterproof clothing to the event
Appropriately qualified first aid-trained staff will be identified to cover all NFYT activity
First aid equipment will be made available across all NFYT venues
NFYT12 | Campsite based injury relating to electrics and Get in/out activity | 5 | 3 | 15 | All equipment fit up and rigging will be undertaken by qualified professional staff | 5 | 2 | 10 | CEO/ Production Manager/ Projects Producer | CEO
All equipment used is in good working order and to current safety standards
All staff will be made aware of routes vehicles will use and staff will ensure routes are clear
PLI and PAT certificates will be obtained for all electrical items on campsite supplied by contractors and festival partners
Areas thats are not suitable for public will be taped off eg. around the generator / where pipes run.
Appropriately qualified first aid-trained staff will be identified to cover all NFYT activity
First aid equipment will be made available across all venues
NFYT13 | Fire at the campsite | 5 | 3 | 10 | NFYT operates a strict no-fire policy across the entire campsite. Open flames of any description are prohibited, including camping stoves, BBQs, gas lanterns, candles, cigarette lighters and matches | 5 | 1 | 5 | CEO/ Production Manager/ Projects Producer | CEO
The festival is completely smoke-free; smoking and vaping are not permitted anywhere on site at any time
No food preparation or cooking takes place on the campsite — all catering is served at Eden Court Theatre
The only fuel-powered equipment on site is the generator, which is installed, operated and maintained by approved contractor Limelight, and the Production Manager. It's cordoned off and strictly out of bounds to all participants at all times
The campsite code of conduct, communicated to all participants and group leaders in advance and on arrival, explicitly prohibits all sources of ignition
The Grandstand and Pavilion buildings have existing fire alarm systems managed by High Life Highland
Appropriately qualified first aid-trained staff will be on site at all times
An overnight security guard is responsible for enforcing the no-fire policy and for activating the alarm and initiating evacuation in the event of a fire

## Draft (hidden)
Youth Theatre Arts Scotland Risk Register |  | Last updated:
Organisational Risk Register
Risk Scores: 0-5 = Low Risk 6-9 = Medium Risk 10-15 = High Risk 16-25 = Very High Risk
Assessment |  |  |  |  | Planning and Implementation |  |  | Notes and updates
Code | Identified Risk (Description of risk to be managed) | Impact 1 - 5 (5 = most severe) | Probability 1 - 5, ( 5 = most probable) | Risk Score (probability x Impact = Priority) | Planned Response (Description of how the risk will be managed) | Risk Owner (person(s) responsible) | Monitoring (timescales, costs, plans)
Strategic
Strat1 | Inability to implement Business Plan |  |  |  | Regular project planning meetings; Board and Funder reviews | CEO & GM | Board
Strat2 | Inability to effectively communicate our aims and objectives and secure necessary support (CS) |  |  |  | keep up to date with internal changes; maintain up to date information and existing relationships | CEO & GM | Board
Strat3 | Inability to broaden relationships with key national stakeholders |  |  |  | Develop strategy within new Business Plan | CEO & GM | Board
Strat4 | Changes in Government/government policy |  |  |  | Develop new connections and continues to make the case for children and young people's performing arts | CEO & GM | Board
Staff
Staff1 | Loss of key staff and structural changes |  |  |  | Annual appraisals; succession planning; competitive terms. | CEO & GM | Board
Staff2 | Lack of relevant policies and procedures |  |  |  | Use relevant agencies to keep up to date with changes and implement change when required | GM | Board
Staff3 | Lack of opportunity for personal and professional development for staff |  |  |  | Annual appraisals; maintain training budget; opportunities to take part in Creative Development Activities; develop more pro-active approach | GM | Board
Operational
Ops1 | Venues and LAs do not support YTAS national events |  |  |  | Maintain positive relationships; maintain quality of event management | GM & PC | Board
Ops2 | Failure of IT systems |  |  |  | External back-up and professional support in place. | GM & AC | Board
Ops3 | Failure of telecommunication systems |  |  |  | Email and mobile phones as alternative | GM & AC | Board
Ops4 | Failure of systems/management at organisation's premises |  |  |  | Ensure ability to work remotely; maintain regular contact with landlord | GM & AC | Board
Financial
Fin1 | Inability to find alternative sources of private funding to support the programme |  |  |  | Establish and seek advice on new sponsorship pack; create list of key contacts; seek alternative sources of inc. | Board, CEO & MCD, GM | Board
Fin3 | Inability to identify and approach replacement project funds |  |  |  | Continuous research; use existing connections and make new ones | CEO & GM | Board- Ongoing research
Fin5 | Loss of secure, regular funding from CS |  |  |  | Improve communication with key personnel; regular evaluation reports; prepare funding application for July deadline | Board, CEO & GM | Board - Ongoing
Fin6 | Inability to maintain sufficient reserves |  |  |  | Monitor budgets closely; regular reporting to the Board. | GM | Board
Reputation/Image
Rep1 | Sector doesn't develop |  |  |  | Seek alternative funding streams and new partners; Continue to lobby funders; produce good quality research and advocacy documents | CEO & GM | Board
Rep2 | Organisation cannot develop its role |  |  |  | Continue to lobby funders; produce good quality research and advocacy documents. Review and develop organisation's role with staff and Board. | CEO & GM | Board
Rep3 | Press and critical coverage reduces |  |  |  | Maintain key contacts; produce good quality information | GM & CD | Board
Rep4 | Negative perceptions within sector damage overall reputation of organisation |  |  |  | Discuss at Board level; improve consultation and communication with the sector and key funders | GM & CD | Board
External/Political
Ext1 | Changes in CS policies/priorities |  |  |  | Improve communication with key personnel; regular evaluation reports | Board, CEO & GM | Board - Ongoing
Ext2 | Changes to LA policies/priorities |  |  |  | Continue to make the case for children's performing arts | CEO | Board
Ext3 | Changes in Government (Scotland & UK) |  |  |  | Develop contacts/relationships with key politicians and civil servants | CEO | Board